## Observation Register
Observation ID | Audit Name | Audit Period | Department / Process | Observation / Finding | Risk Rating | Root Cause | Recommendation / Action Plan | Action Owner | Original Due Date | Revised Due Date | Extension Count | Extension Reason | Effective Due Date | Status | Closure Date | Closure Evidence | Validation Status | Validated By | Validation Date | Days Open | Days Overdue | Aging Bucket | Remarks
OBS-001 | ITGC Audit | Q2 2026 | Access Management | Periodic user access review evidence was not available. | High | Review ownership was not clearly assigned. | Establish quarterly access review and retain evidence. | IT Manager | 2026-07-15 | 2026-07-31 | 1 | Extension approved due to remediation dependency. |  | In Progress |  |  | Pending
OBS-002 | Internal Audit | Q2 2026 | Vendor Management | Annual vendor reassessment was overdue for selected vendors. | Medium | Tracking was maintained manually. | Implement a centralized vendor reassessment tracker. | Vendor Risk Owner | 2026-08-01 |  | 0 |  |  | Open |  |  | Pending
Formulas:
Days Open = IF([Observation ID]="","",IF([Closure Date]<>"",[Closure Date]-[Original Due Date],TODAY()-[Original Due Date]))
Days Overdue = IF([Observation ID]="","",IF(OR([Status]="Closed",[Effective Due Date]=""),0,MAX(0,TODAY()-[Effective Due Date])))

## Dashboard
Audit Observation Dashboard
Total Observations | Risk Rating | Count | Status | Count
Open | Critical |  | Open
In Progress | High |  | In Progress
Pending Validation | Medium |  | Pending Validation
Closed | Low |  | Closed
Overdue |  |  | Deferred
High / Critical
Average Days Open

## Instructions
Field / Topic | Guidance
Purpose | Use this workbook to track audit observations from identification through remediation, validation, and closure.
Effective Due Date | The Revised Due Date is used when populated; otherwise the Original Due Date is used automatically.
Extension Count | Record the number of approved due-date extensions.
Days Overdue | Calculated automatically against the Effective Due Date for non-closed observations.
Aging Bucket | Calculated from Days Open: 0–30, 31–60, 61–90, and 90+ days.
Closure Evidence | Record the evidence or reference supporting remediation completion.
Validation Status | Use Pending, Pass, Fail, or Not Required. Closure should be validated according to your audit methodology.
Status | Recommended lifecycle: Open → In Progress → Pending Validation → Closed. Deferred may be used where formally approved.
Important | Replace the sample observations before using the tracker for live data.